## Tool Summary Sheet
Tool Summary Sheet
| Tool: | Start-Up Timeline Calculator Basic Elements
| Purpose: | To provide a starting point for timelines associated with study / site activation
| Audience/User: | Principal Investigators, Study Coordinators, and CROMS
| Details: | This tool is intended to provide a framework for start-up timelines based on average durations for common components of site activation. This workbook has the following tabs: 1-Tool Summary, 2-NIDCR-CROMS Timeline Calculator. This Tool Summary Sheet will provide instructions for using the NIDCR-CROMS Timeline Calculator.
| Best Practice Recommendations: | The Timeline Calculator identifies typical tasks and their average timelines associated with the start-up of clinical studies. In order to calculate estimated start-up timeline, enter the date of award notification, or other date used as the starting reference point, in the yellow bolded box (E3 on the Timeline Calculator tab). All other dates will populate automatically. An appropriate alternative milestone may be selected for start date. Once the milestone date has been entered, the entire timeline will be summarized in the Start Date and Finish Date Columns (E2 and F2). Additionally, the duration of the protocol development task may be changed to provide a more accurate representation of the start-up timeline. TO NOTE: In order to facilitate the use of timeline formulas, all calculations are done in days. The durations entered will be in portions of a month (Column C), however in order to arrive at a finish date, this is then converted to days (Column D). Additionally, all cells are restricted from entry with the exception of the bold yellow cells.
Tool Revision History:
Version Number | Version Date | Summary of Revisions Made:
1 | 2012-04-30 | First approved version
2 | 2021-10-21 | Routine review; updated logo and included CROMS in title of tool.

## NIDCR-CROMS Timeline Calculator
Item/Task |  | Duration of Task 1 mo. = 30 days .75 mo=22.5 .5 mo=15 days .235 mo=7 days .2 mo=6 days .05 mo=2 days (can be changed) | Days (=C*30) | Start Date | Finish Date | Predecessor Task FS=task indicated in this column must finish prior to start of current task line SS=tasks can both start on the same day and run in parallel (can be changed)
| Award Notification to First Subject Enrolled Totals: |  | 259.5 | 2021-09-20 | 2022-06-06 12:00
1 | Notice of Award Received |  | 0 | 2021-09-20 | 2021-09-20 | NA | **START HERE** For first draft of timeline based on average durations: Enter date in yellow box to populate all other dates
2 | Protocol Development to Final Draft (Includes protocol development and vetting through NIDCR. Time presented is an average based on experience. Can be longer or shorter based on status of protocol at award.) | 2 | 60 | 2021-09-20 | 2021-11-19 | 1 FS | An actual representation of your protocol development time can be entered here to more accurately reflect your timeline based on the variability of this task.
3 | Submit final draft protocol and consent document to NIDCR for review and comment; incorporate revisions | 0.05 | 1.5 | 2021-11-19 | 2021-11-20 12:00 | 2 FS
4 | NIDCR Review of Final Draft | 0.5 | 15 | 2021-11-20 12:00 | 2021-12-05 12:00 | 3 FS
5 | Oversight Committee Review of Protocol (if applicable) | 0.5 | 15 | 2021-12-05 12:00 | 2021-12-20 12:00 | 4 FS
6 | Protocol & Consent Document Finalization (Includes review, comment and recommendations by DSMB/CSOC.) | 2 | 60 | 2021-12-20 12:00 | 2022-02-18 12:00 | 5 FS
7 | Submission & Approval of Protocol & Consent Documents to necessary IRBs (Assumes single site with one IRB.) | 1.5 | 45 | 2022-02-18 12:00 | 2022-04-04 12:00 | 6 FS
8 | Preparation and submission of IND (if applicable) (Minimum of 30 days must elapse between submission of IND and beginning of enrollment. IRB may request documentation of IND approval prior to issuing final IRB approval.) | 2 | 60 | 2021-12-20 12:00 | 2022-02-18 12:00 | 6 SS
9 | Data Management & Safety Management Tasks for Site Activation (This time includes creation of source documents, CRFs, designing and implementing a database, (EDC or a paper study) training on the data system, setting up safety reporting (SAEs), and all associated Plans.) | 2.25 | 67.5 | 2022-03-04 12:00 | 2022-05-11 | 7 SS +14 days
10 | Site Staff Preparation (Time includes writing a Manual of Procedures, assessing SOPs, training staff on protocol, specimen collection, processing, storage and shipping, study time and events tables, full protocol training identification of site staff for study roles.) | 3 | 90 | 2022-02-18 12:00 | 2022-05-19 12:00 | 7 SS
11 | Site Facility Preparedness (Includes collection of necessary supplies, assuring physical facilities meet privacy and security standards as well as any labs meeting requirements per protocol, for example: appropriate specimen processing equipment, freezers, centrifuges etc.) | 1.5 | 45 | 2022-02-18 12:00 | 2022-04-04 12:00 | 7 SS
12 | Study Product Ready on Site (if applicable) (Time includes identification of study product supplier, calculating amount of study product needed, ordering study product, shipment prior to Site Initiation Visit, QC of received product, development of process for study product distribution to patients.) | 3 | 90 | 2022-02-18 12:00 | 2022-05-19 12:00 | 6 FS
13 | Site Initiation Visit/Teleconference | 0.05 | 1.5 | 2022-05-19 12:00 | 2022-05-21 | 6FS, 7FS, 8FS, 9FS, 10FS, 12FS
14 | Activation Action Item Tracker Completed | 0.5 | 15 | 2022-05-21 | 2022-06-05 | 9 FS
15 | Site is Activated | 0.05 | 1.5 | 2022-06-05 | 2022-06-06 12:00 | 10 FS